## How to use
Dissertation and thesis Gantt chart template
Free from Trawpie. Undergraduate, master’s and PhD sheets: pick the tab for your level.
How to use it
1. Type your start date and hand-in (or thesis submission) date in the two yellow cells at the top of your sheet.
2. Every date in the plan moves with them: tasks are spread across your time in proportion, the way the plan suggests.
3. Type over any start or end date to fix it to your university’s real deadline (proposal, ethics, draft to supervisor).
4. Set each task’s Status as you go. Done turns the bar green; anything not done after its end date turns orange.
5. The yellow column is this week (this month on the PhD sheet). ◆ marks a milestone.
6. Add your own tasks in the empty rows at the bottom: give them a Type, a start and an end date, and the bars appear.
Good to know
Not working with people? Delete the Ethics rows and rename the data collection tasks (experiments, a build, a dataset).
Longer than the chart? Copy the last date column to the right as far as you need; the bars follow.
Dates are proposals, not rules: agree the plan with your supervisor and change it as you learn more.
Opening in Google Sheets: File ▸ Import ▸ Upload, then Replace spreadsheet. The colours and formulas come with it.
Rather have it done for you?
Trawpie makes this plan from your hand-in date in about a minute, then keeps it live: tasks with checklists, chapter word counts, a proposal helper, supervisor meetings, draft feedback and reminders in your calendar. Free for students.
https://trawpie.org/dissertation

## Undergraduate
Undergraduate dissertation Gantt chart
Free template from Trawpie: trawpie.org/dissertation
Start date |  | 2026-09-28 |  | ← type your dates in the yellow cells; every date below moves with them
Hand-in date |  | 2027-04-30
Today |  |  |  | Key: |  |  | Phase |  |  |  | Task |  |  |  | Done |  |  |  | Late |  |  |  | Milestone ◆ |  |  |  | This week
[5 empty] | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Task | Type | Start | End | Days | Status
Topic and proposal | Phase
First meeting with your supervisor | Task |  |  |  | Not started
Choose a topic and a working question | Task |  |  |  | Not started
Write the proposal | Task |  |  |  | Not started
Proposal submitted | Milestone |  |  |  | Not started
Ethics approval | Phase
Check what ethics approval you need | Task |  |  |  | Not started
Prepare the ethics application | Task |  |  |  | Not started
Ethics approved | Milestone |  |  |  | Not started
Literature review | Phase
Set up your reading list | Task |  |  |  | Not started
Search for sources | Task |  |  |  | Not started
Read and take notes on the key sources | Task |  |  |  | Not started
Write: Literature review | Task |  |  |  | Not started
Methodology | Phase
Choose your methods and say why | Task |  |  |  | Not started
Write: Methodology | Task |  |  |  | Not started
Data collection | Phase
Recruit participants | Task |  |  |  | Not started
Pilot your interview or survey | Task |  |  |  | Not started
Collect the data | Task |  |  |  | Not started
Transcribe and store the data securely | Task |  |  |  | Not started
Analysis | Phase
Analyse your results | Task |  |  |  | Not started
Make the figures and tables | Task |  |  |  | Not started
Write: Results | Task |  |  |  | Not started
Writing | Phase
Write: Discussion | Task |  |  |  | Not started
Write: Conclusion | Task |  |  |  | Not started
Write: Introduction | Task |  |  |  | Not started
Full draft to supervisor | Milestone |  |  |  | Not started
Revisions and proofreading | Phase
Work through your supervisor’s feedback | Task |  |  |  | Not started
Check references and citations | Task |  |  |  | Not started
Proofread (read it aloud) | Task |  |  |  | Not started
Formatting and hand-in | Phase
Format to your department’s guidelines | Task |  |  |  | Not started
Hand in your dissertation | Milestone |  |  |  | Not started

## Masters
Master’s dissertation Gantt chart
Free template from Trawpie: trawpie.org/dissertation
Start date |  | 2027-05-24 |  | ← type your dates in the yellow cells; every date below moves with them
Hand-in date |  | 2027-09-10
Today |  |  |  | Key: |  |  | Phase |  |  |  | Task |  |  |  | Done |  |  |  | Late |  |  |  | Milestone ◆ |  |  |  | This week
[5 empty] | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Task | Type | Start | End | Days | Status
Topic and proposal | Phase
First meeting with your supervisor | Task |  |  |  | Not started
Choose a topic and a working question | Task |  |  |  | Not started
Write the proposal | Task |  |  |  | Not started
Proposal submitted | Milestone |  |  |  | Not started
Ethics approval | Phase
Check what ethics approval you need | Task |  |  |  | Not started
Prepare the ethics application | Task |  |  |  | Not started
Ethics approved | Milestone |  |  |  | Not started
Literature review | Phase
Set up your reading list | Task |  |  |  | Not started
Search for sources | Task |  |  |  | Not started
Read and take notes on the key sources | Task |  |  |  | Not started
Write: Literature review | Task |  |  |  | Not started
Methodology | Phase
Choose your methods and say why | Task |  |  |  | Not started
Write: Methodology | Task |  |  |  | Not started
Data collection | Phase
Recruit participants | Task |  |  |  | Not started
Pilot your interview or survey | Task |  |  |  | Not started
Collect the data | Task |  |  |  | Not started
Transcribe and store the data securely | Task |  |  |  | Not started
Analysis | Phase
Analyse your results | Task |  |  |  | Not started
Make the figures and tables | Task |  |  |  | Not started
Write: Results | Task |  |  |  | Not started
Writing | Phase
Write: Discussion | Task |  |  |  | Not started
Write: Conclusion | Task |  |  |  | Not started
Write: Introduction | Task |  |  |  | Not started
Full draft to supervisor | Milestone |  |  |  | Not started
Revisions and proofreading | Phase
Work through your supervisor’s feedback | Task |  |  |  | Not started
Check references and citations | Task |  |  |  | Not started
Proofread (read it aloud) | Task |  |  |  | Not started
Formatting and hand-in | Phase
Format to your department’s guidelines | Task |  |  |  | Not started
Hand in your dissertation | Milestone |  |  |  | Not started

## PhD
PhD thesis Gantt chart
Free template from Trawpie: trawpie.org/dissertation
Start date |  | 2026-10-01 |  | ← type your dates in the yellow cells; every date below moves with them
Thesis submission |  | 2030-03-29
Today |  |  |  | Key: |  | Phase | Task | Done | Late | Milestone ◆ | This month
Year
Task | Type | Start | End | Days | Status
Literature review and research questions | Phase
Set up your reading list | Task |  |  |  | Not started
Systematic search of the literature | Task |  |  |  | Not started
Write your research questions | Task |  |  |  | Not started
First draft of the literature review | Task |  |  |  | Not started
Research plan and training | Phase
Agree a research plan with your supervisors | Task |  |  |  | Not started
Training: methods courses and research integrity | Task |  |  |  | Not started
Ethics approval | Phase
Prepare the ethics application | Task |  |  |  | Not started
Ethics approved | Milestone |  |  |  | Not started
Pilot study | Phase
Run a small pilot study | Task |  |  |  | Not started
Write up the pilot (it becomes part of your upgrade report) | Task |  |  |  | Not started
Upgrade / confirmation review | Phase
Write the upgrade report | Task |  |  |  | Not started
Upgrade / confirmation review | Milestone |  |  |  | Not started
Main studies | Phase
Study 1: plan and set up | Task |  |  |  | Not started
Study 1: collect the data | Task |  |  |  | Not started
Study 1: analyse and write up | Task |  |  |  | Not started
Study 2: plan and set up | Task |  |  |  | Not started
Study 2: collect the data | Task |  |  |  | Not started
Study 2: analyse and write up | Task |  |  |  | Not started
Annual progress review (year 2) | Milestone |  |  |  | Not started
Study 3: plan and set up | Task |  |  |  | Not started
Study 3: collect the data | Task |  |  |  | Not started
Study 3: analyse and write up | Task |  |  |  | Not started
Annual progress review (year 3) | Milestone |  |  |  | Not started
Papers and conferences | Phase
Write a paper from your first study | Task |  |  |  | Not started
Present at a conference | Task |  |  |  | Not started
Writing up | Phase
Write: Literature review | Task |  |  |  | Not started
Write: Methodology | Task |  |  |  | Not started
Write: Discussion | Task |  |  |  | Not started
Write: Conclusion | Task |  |  |  | Not started
Write: Introduction | Task |  |  |  | Not started
Full thesis draft to supervisors | Milestone |  |  |  | Not started
Revisions | Phase
Work through your supervisors’ comments | Task |  |  |  | Not started
Check references, figures and formatting | Task |  |  |  | Not started
Submission | Phase
Submit your thesis | Milestone |  |  |  | Not started
Viva and corrections | Phase
Prepare for your viva | Task |  |  |  | Not started
Viva | Milestone |  |  |  | Not started
Corrections | Task |  |  |  | Not started